## Slide 1: Project Kestrel: Q3 2026 Review
Halcyon Robotics · Automated inspection program
Prepared for the leadership review, 6 October 2026
Notes: Kestrel is the program that moved our utility inspections from manual drone piloting to scheduled autonomous missions.

## Slide 2: Q3 goals
Scale autonomous inspections to 1,400 sites per quarter
Raise defect detection recall above 90%
Launch the customer reporting portal
Keep total program spend under budget
Notes: We hit three of the four goals; the portal slipped to Q4.

## Slide 3: Key results
Sites inspected: 1,450 (up 22% quarter over quarter)
Defect detection recall: 91.3% (target 90%)
Average mission time: 26 minutes
Customer NPS: 47 (Q2: 41)
Notes: Recall is measured on the labelled validation set of 4,800 images reviewed by our senior inspectors.

## Slide 4: Model improvements
Retrained the defect detector on 31,000 new labelled images
Added thermal hot-spot classifier for transformers
False positives per 100 images fell from 6.1 to 3.8
Notes: The thermal classifier runs on the Talon-3 rover's thermal camera as well as on the HX-7.

## Slide 5: Budget
Approved FY2026 budget: $3.1M
Spent through Q3: $2.4M
Largest cost: field crew hours (46%)
Hardware: 18 new HX-7 units purchased
Notes: We expect to finish the year about $150K under budget if the LiDAR deliveries arrive as planned.

## Slide 6: Risks
Supply chain: the LX-200 LiDAR module has a 14-week lead time
Two crews are below staffing target in the North region
Telemetry reliability after INC-2047
Notes: We placed a buffer order of 25 LX-200 modules in September to cover Q1 2027 builds.

## Slide 7: Incident follow-up: INC-2047
August telemetry outage took 312 robots offline
Certificate renewal is now automated
Alerting threshold reduced to 3 minutes
Notes: All high-priority action items from the postmortem are closed except the gateway failover drill.

## Slide 8: Customer reporting portal
Status: slipped to Q4
Beta with three utility customers
Exports inspection findings as PDF and CSV
Notes: The delay came from the security review requested by our largest customer.

## Slide 9: Next steps for Q4
Launch the reporting portal to all customers
Start a pilot with a new water utility in November
Hire 6 more field operators for the North region
Run the gateway failover drill
Notes: The November pilot customer is Brightwater Utilities, covering 220 pumping stations in two counties.

## Slide 10: Team and contacts
Program lead: Mara Okafor
Head of ML: Daniel Reyes
Field operations: Priya Natarajan
Questions: kestrel-program channel
Notes: Mara Okafor took over as program lead in July after the reorganization.